## Sheet1
Project Name: Application For Vaccine Registration |  | Presented by: Swetha Gahana |  | Date: | 2020-05-23
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 25 | 20 | 500 |  |  | 0 | 500 |  | 500
2. Planning | 50 | 20 | 1000 |  |  | 0 | 1000 |  | 1000
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Course design and development |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Supplier management training | 5 | 20 | 100 | 10 | 20 | 100 | 200 | 800 | 1000
3.1.2 Negotiating skills training | 5 | 20 | 100 | 10 | 20 | 100 | 200 | 800 | 1000
3.1.3 Project management training | 5 | 20 | 100 | 10 | 20 | 100 | 200 | 800 | 1000
3.1.4 Software applications training | 5 | 100 | 500 | 10 | 100 | 500 | 1000 | 4000 | 5000
3.2 Course administration | 5 | 80 | 400 | 10 | 80 | 400 | 800 | 3200 | 4000
3.3.Course evaluation | 25 | 20 | 500 |  |  | 0 | 450 |  | 450
3.4 Stakeholder communications | 10 | 150 | 1500 |  |  | 0 | 1500 |  | 1500
4. Monitoring and Controlling | 25 | 80 | 2000 |  |  | 0 | 2000 |  | 2000
5. Closing | 25 | 20 | 500 |  |  | 0 | 550 |  | 550
Subtotal | [8 empty] | 18000
Reserves |  |  | 0 |  |  | 0 | 0 |  | 2000
Total | 185 |  | 7200 | 50 | 240 | 1200 | 8400 | 9600 | 20000
Assumptions: We are expecting our overall budget around 18000$ with reserves at 10 % which accounts to total of 20000$ |  | % which accounts to total of 20,000$